## TPP list
Seznam objednávek vzorků a prototypů válcovaných produktů
List of Orders and roll bonding prototypes
One line [No] => One order position
One order => one RPP
| Today: | 2025-09-17
Status | Internal order number | Customer | Project | MDS Revision | Submitted by | Product name | Purpose | Qty | Customer order number | Order date | Requested date | Delivered on | Worker | Next step | Remark | Lesson learnt from production built/Comment
G | RPP - K24010 | Ford | BEV-K 2P28S | TBS | Marcel Eifler | Rb Part - coating | 2P28S NOK with leak / no leak only channels and scrateches issue | 20 |  | 2024-12-10 | 2025-02-07 | 2025-02-25 | Slavomir Majcher | Prepared for shipping | Packed, prepared for shipping by DHL FORD - Georg needs to confirm PO
G | RPP - K24011 | Ford | BEV-K 2P36S | TBS | Marcel Eifler | Rb Part - coating | 2P36S NOK with leak / no leak only channels and scrateches issue | 20 |  | 2024-12-10 | 2025-02-07 | 2025-02-25 | Slavomir Majcher | Prepared for shipping | Packed, prepared for shipping by DHL FORD - Georg needs to confirm PO
G | RPP - K250002 | Ford | BEV-K 3P24S | N/A | Marcel Georg | Rp Part - welded spigots | Lennard COMP Parts , NOK but tight 3P24S | 8 |  | 2025-01-08 | 2025-01-24 | 2025-02-25 | Slavomir Majcher | shipping address to be clarified | DHL scheduled by FORD - Prepared for Lennard / FORD and packed 23.1.2025
G | RPP - K250003 | Ford | BEV-K 2P36S | N/A | Marcel Georg | Rp Part - welded spigots | Lennard COMP Parts , NOK but tight 2P36S | 7 |  | 2025-01-08 | 2025-01-24 | 2025-02-25 | Slavomir Majcher | shipping address to be clarified | DHL scheduled by FORD - Prepared for Lennard / FORD and packed 23.1.2025
G | RPP - K250006 | SK | BEV-K 2P36S | N/A | Marcel Georg | Rp Part - welded spigots | SK - not ordered yet – Additional Parts uncoated 2P36S | 20 |  | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV
G | RPP - K250007 | Ford | BEV-K 3P24S | N/A | Marcel Georg | Rb Part - coating | FORD - 4499247- David Doman Parts - 3P24S | 63 |  | 2025-01-08 | 2025-03-21 | 2025-02-10 | Slavomir Majcher | Production in hall 3 - tools validation needed
G | RPP- K250004 | SK | BEV-K 2P36S | N/A | Marcel Georg | Rb Part - coating | 2P36S - PO 4200118980 /DCV/ -SK | 124 |  | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV
Y | RPP- K250021 | Ford | BEV-K 2P36S | B01 | Marcel Georg | Rb LC | Special customer demand - different contour, no Inf, no welding | 12 |  | 2025-03-28 | 2025-09-23 |  | Slavomir Majcher | HP, laser cutting SLT different contour - Update (22.5.2025): missing customer PO - waiting for it - Update (4.6.2025): still waiting for PO - update 30.6.2025 : 2 pcs were sold for MOA shipped CW27 and 2pcs were sold for Precitec shipped CW29. Rest qty no PO yet. 4pcs are compleded to 12cps of qty CW38 | without PF,Inf, CC, welding . Only HP and separation , special contour Lacer cut
CANCELED | RPP- K250022 | Ford | BEV-K 2P36S | B01 | Marcel Georg | Rb CC | Special customer demand - , no Inf, no welding - Fatugue test | 4 |  | 2025-03-28 | 2025-07-04 | 2025-09-17 | Slavomir Majcher | HP, CC - Update (22.5.2025): missing customer PO - waiting for it - Update (4.6.2025): still waiting for PO - Update (11.6.2025): still waiting for PO - on old | without PF,Inf, welding . Only HP and separation and CC
G | RPP-K240001 | Scania | GBP2 | N/A | Deng Guoyu | Coupons | Samples for Att laser cut | 45 |  | 2024-12-05 | 2024-12-12 | 2024-12-11 | Daniel Cuc |  | Shipped WGM4489H together with Audi and Scania to SLT
G | RPP-K240002 | Internal | Daimler Showplate | A06 | Marcel Eifler | RbPart - coating | Shanghai Autoshow exhibition | 10 | Kosice orders all | 2024-12-01 | 2025-02-15 | 2025-01-09 | Daniel Cuc | To be shipped back | Shipped to Weba
G | RPP-K240003 | Mercedes | Test Rack | C00 | Robert Schneider | RbInf | Lab plates | 150 |  | not yet | 2025-02-07 | 2025-02-07 | Daniel Cuc |  |  | missing delivery note
G | RPP-K240004 | QMC | Unknown | E00 | Brian Wilson | Rb Inf + cut for shipment | B-samples | 150 |  | 2024-12-01 | 2024-12-19 | 2025-12-19 | Daniel Cuc |  | 150 parts shipped out in 5 boxes
G | RPP-K240005 | CATL | Unknown | N/A | Deng Guoyu | Other | Material samples | 30 |  | 2024-12-02 | 2025-01-07 | 2025-01-07 | Daniel Cuc |  | Shipped out, delivery note in the folder
G | RPP-K240006 | Internal | BEV-K 2P36S | B01 | Mike DeGregory | Rb Inf | 2P36S Engineering centre Auburn Hills | 300 |  | 2024-12-10 | 2025-03-08 | Canceled | Slavomir Majcher | start RB CW4 | open point - MDS DCV uppdate Mike De Gregory - approved serial B01(D01)
G | RPP-K240007 | Ford | BEV-K 2P36S | TBS | Marcel Eifler | Rb Part - coating | 2P36S Customer | 500 |  | 2024-12-10 |  | Canceled | Slavomir Majcher | start RB CW4 | open point - MDS Marcel Eifler - B01(D01)
G | RPP-K24008 | Internal | BEV-K | N/A | Andreas Muller | Rb Inf | 2P36S NOK | 200 |  | 2024-12-13 | 2025-01-17 | 2025-01-14 | Slavomir Majcher |  | parts handed over to welding machines for trials
G | RPP-K24009 | Internal | BEV-K | N/A | Marcel Eifler | Rb Inf | 2P36S NOK | 60 |  | 2024-12-17 | 2025-01-17 | 2025-01-21 | Slavomir Majcher | select parts and prepare for shipment | Sent to Kemper / batch to Vogler coating test/
G | RPP-K250001 | Internal | Material test | A00 | Lennart Rietz | Rb Blank | Test material 3D forming | 60 |  | 2025-01-07 | 2025-03-31 | 2025-04-04 | Daniel Cuc |  | sent on 4.4.2025 | MDS released without information, we were unable to use water inflation
G | RPP-K250005 | SK | BEV-K 2P28S | N/A | Marcel Georg | Rb Part - coating | 2P28S - PO 4200118980 /DCV/ -SK | 60 |  | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV
G | RPP-K250008 | Internal | Bionical Showplate | A00 | Frederik Schrewe | Rb Cut - scissors | Prototype showplatee Shanghai | 20 |  | 2025-12-09 | 2025-01-31 | 2025-02-07 | Daniel Cuc | get delivery note |  | too long plates, no packaging available
Y | RPP-K250009 | Internal | Renault | N/A | Bjoern/Markus Wolf | Rb Inf | For development department | 23 |  | 2025-01-10 | 2025-09-29 |  | Daniel Cuc | Send the parts A,B,C,D, G to measurement, rest plan for next Renault production - Update (4.6.2025): Email Conversation with Bjorn + Dan = we need to make it on next production loop (maybe July) - Update - run with next Renault production | Delivery date postponed to 15th February, due two updates and miscommunication | Wrong communication, many misunderstanding, clear process flow is necessary, 2 uncontroll updates
G | RPP-K250010 | Internal | BEV-K | B01 | Björn Scholemann | Various |  | 18 |  | 2025-01-15 | 2025-01-31 | 2025-03-25 | Daniel Cuc | Check where they are when come back from Attendorn
G | RPP-K250011 | Internal | BEV-K 2P36S | B01 | Björn Scholemann | Rp Part - welded spigots | V29 HP tools test - ATT test of HP hole /penetration channels | 28 |  | 2025-01-31 | 2025-02-14 | 2025-03-13 | Slavomir Majcher | CW6.5 V29 tool broken / repair + spare partsreceived CW6 for test, PRO did leveling 10blanks CW6. HPtool test 10 blanksCW9.2 in Hall2 . Next PF/Inf/CC/weld - process flow hall3
G | RPP-K250012 | Internal | Renault | N/A | Marcel Eifler | Rb Blank | Renault 120blanks w/o screen print , leveled - old stock from hall4 | 120 |  | 2025-02-05 | 2025-02-14 | 2025-02-10 | Slavomir Majcher | Checked stock - 81 bl available 1520x1300 x 3 . Looks w/o - leveling done CW6 - PO Marcel E. | Checked stock - 81 bl available 1520x1300 x 3 . Needs to mesure tickness 1.2+1.5
G | RPP-K250013 | Internal | BEV-K 2P28S | N/A | Antonius Hutte | Rb CC | Demand 1+4 pcs for internal test from process flow hall3 | 5 |  | 2025-02-05 | 2025-02-14 | 2025-02-17 | Slavomir Majcher | sent 2 cut streap batches urgent to ATT by air CW6.5. Rest need to confirm by Antonius | Vulkan Engineering GmbH - 1 pc , Mubea Tailor Rolled Blanks GmbH z.Hd. Hütte, Antonius - 4 pcs
G | RPP-K250014 | Internal | BEV-K 2P36S | N/A | Marcel Eifler | Rb CC | Internal test | 15 |  | 2025-02-06 | 2025-02-14 | 2025-02-10 | Slavomir Majcher | red area w/o spigot an lacer cut done - , CC will be in hall3 CW7 | NOK 15pcs 28S or 36S coling plates w/o spigot demand , CC or laser cut demand needs to check from Marcel
CANCELED | RPP-K250015 | Internal | BEV-M | N/A | Björn Scholemann | Various | Investigation Holepunching; BEV-M; 0.5mm groove depth | 28 |  | 2025-02-05 | 2025-02-28 | 2025-04-03 | Daniel Cuc |  |  | canceled, not even knowing how
G | RPP-K250016 | Renault | Flex E-Van | N/A | Olivier Billot | Coupons | Coupons for customer | 30 |  | 2025-03-03 | 2025-07-23 | 2025-07-24 | Daniel Cuc | parts shipped out to customer | each part has differrent process
G | RPP-K250017 | Internal | BEV-M | N/A | Bjoern Scholemann | Rb Inf | Leveling investigatin, various configurations based on list | 20 |  | 2025-01-09 | 2025-03-06 | 2025-03-10 | Daniel Cuc |  | Confirmation about shipment missing due to system not set up yet | parts lost, then found again due to no activity, need better tracking
G | RPP-K250018 | Volvo | EX40 | A00 | Julian Sieler | Rb Inf | Customer part presentation | 15 |  | 2025-03-19 | 2025-04-09 | 2025-04-04 | Daniel Cuc |  | sent on 4.4.2025 | parts lost, then found again due to no activity, need better tracking
G | RPP-K250019 | GM | Material test | N/A | Raneem | Coupons | Material samples in US | 15 |  | 2025-03-19 | 2025-04-09 | 2025-04-04 | Daniel Cuc | sent on 4.4.2025 - Update (22.5.2025): need to separate cupons - Update (4.6.2025): we will cut on Friday (6.6.2025) and after that send it Raneem - Update (10.6.2025): coupons are deburred and ready to shipping - waiting for PO from Raneem |  | well communicated from US, smooth production
G | RPP-K250020 | Ford | BEV-M | C00 | Marcel Eifler | Rb Blank | Parts without screen prints | 50 |  | 2025-03-26 | 2025-04-09 | 2025-04-01 | Daniel Cuc |  | Delivered to Marcel Eiffler | parts lost, then found again due to no activity, need better tracking
G | RPP-K250023 | Internal | Flex E-Van | F01 | Li Lei | Rb Blank | RB speed 12m/min, detailed analysis | ?? |  | 2025-04-09 | 2025-04-25 | 2025-05-27 | Marek Drotar | Receive instruction from Li Lei, Update (22.5.2025): Due date: 23.5.2025 | Marek Drotar has made the parts during the run for himself and tested furter
G | RPP-K250024 | Internal | Flex E-Van | F01 | Kevin Koch | Rb Inf | Parameter study inflation | 30 |  | 2025-04-29 | 2025-05-30 | 2025-06-19 | Daniel Cuc | Production after R@R on HP+Inflation 28.5.2025 - Update (4.6.2025): Lab works on these pieces - deadline 17.6.2025 - maybe possible earlier 13.6.2025 - Update (19.6.2025): Petra sent email (12:57) about updated study of the inflation parameters
G | RPP-K250025 | Internal | Flex E-Van | F01 | Markus Wolf | Rb Part | Corrosion test | 5 |  | 2025-03-20 | 2025-07-15 | 2025-07-31 | Daniel Cuc | Parts finishted, receive PO from Markus Wolf, prepare for shipment |  | Missing order even after the parts are produced
G | RPP-K250026 | Renault | C-EV | A00 | Olivier Billot | Rb Inf | Acquision parts | 100 |  | 2025-05-01 | 2025-07-24 | 2025-08-15 | Daniel Cuc | Mesurement on GOM done, parts arrived by customer
G | RPP-K250027 | Samsung | E092 | A00 | Robert Schneider | Rb Inf | Acquision parts | 20 |  | 2025-05-29 | 2025-06-30 | 2025-06-30 | Daniel Cuc
G | RPP-K250028 | Internal | Gab-opening samples | A00 | Robert Schneider | Rb Inf | Process Development Material | 20 |  | 2025-05-29 | 2025-06-30 | 2025-07-03 | Daniel Cuc | RB scheduled for week 24
G | RPP-K250029 | Internal | PVT Flat |  | Marek Drotar | Rb Blank | Material reduction during bonding | 10 |  | 2025-06-02 | 2025-07-03 | 2025-07-03 | Tomas Mesaros | Arrange RB with BEV-K, arrange PO - Update (11.6.2025) - waiting for RB BEV-K - 01.07.2025 changed to PVT flat, worker Tomas Mesaros
G | RPP-K250030 | Mercedes | Test Rack | C00 | Robert Schneider | Rb Inf | Parts for customer - second batch | 50 |  | 2025-05-15 | 2025-07-01 | 2025-07-01 | Daniel Cuc | Shippment 1.7., save document
G | RPP-K250031 | TWL | PVT Flat | A01 | Mike DeGregory | Rb Part | Parts for customer - PVT Flat Neumann | 150 |  |  | 2025-07-25 | 2025-08-01 | Tomas Mesaros | - Update (24.6.2025): MDS review
Y | RPP-K250032 | CATL | 390-1 | A00 | Deng Guoyu | Rb Inf | Parts for customer and first trial | 50 |  | 2025-06-19 | 2025-09-15 |  | Slavomir Majcher | 3rd run - inflating parts, delivery date extended. Issue with channel burst and tinning . Inf Investigation . 24pcs inf done
G | RPP-K250033 | Scania | GBP2 | A00 | Deng Guoyu | Rb Inf | Parts for customer | 100 |  | 2025-06-19 | 2025-07-31 | 2025-07-24 | Daniel Cuc | Parts delivered, done
G | RPP-K250034 |  | PVT Flat | A02 | Mike DeGregory | Rb Part | Parts for customer - PVT Flat Flamm | 25 |  |  | 2025-07-25 | 2025-08-26 | Tomas Mesaros | - Update (24.6.2025): MDS review
G | RPP-K250035 |  | PVT Flat | N/A | Marek Drotar | Rb Blank | Minimal roll reduction test |  |  |  | 2025-07-11 | 2025-07-03 | Tomas Mesaros | - Cooperation with Marek
G | RPP-K250037 | MOA | BEV-K 2P36S | N/A | Marcel Georg | RB inf, CC, w/o spigots | Customer welding test | 10 |  | 2025-06-23 | 2025-07-03 | 2025-07-08 | Slavomir Majcher | packing, Shipping CW27
G | RPP-K250038 | Precitec | BEV-K 2P36S | N/A | Marcel Georg | RB inf, film, inlays, w/o spigots | Customer special demand | 6 |  | 2025-06-23 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | cleaning, film, inlys, qc, shipping CW29
G | RPP-K250039 | Internal | BEV-K 2P28S | N/A | Mike DeGregory | Rp Part - welded spigots | NOK parts for suppliers | 5 |  | 2025-06-30 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | goining to ship to ATT CW29
G | RPP-K250040 | Internal | BEV-K 2P36S | N/A | Mike DeGregory | Rp Part - welded spigots | NOK parts for suppliers | 5 |  | 2025-06-30 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | goining to ship to ATT CW29
Y | RPP-K250041 | SK | BEV-K 2P36S | H01 | Marcel Georg | Rb Part | Parts with NOK film simulation for customer _ film issue validation | 10 |  | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | missing PO - free demand - on hold - negotiation wit customer |  | Still missing for PO. Long time waiting (1month)
Y | RPP-K250042 | SK | BEV-K 2P36S | N/A | Marcel Georg | spigots | Short spigots for customer welding test | 35 |  | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | Missing PO - on hold - negotiation price with cutomer |  | Still missing for PO. Long time waiting (1month)
Y | RPP-K250042 | SK | BEV-K 2P36S | N/A | Marcel Georg | spigots | Long and 35pcs short spigots for customer welding test | 35 |  | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | Missing PO - on hold - negotiation price with cutomer |  | Still missing for PO. Long time waiting (1month)
G | RPP-K250043 | Renault | Flex E-Van | N/A | Olivier Billot | Coupons | Coupons for customer | 50 |  | 2025-07-14 | 2025-07-30 | 2025-07-24 | Daniel Cuc | parts shipped out to customer
G | RPP-K250044 | ReBuilt | Slate |  | Brian Wilson | Rb Inf | Parts for customer |  |  | 2025-07-14 | 2025-08-29 | 2025-09-03 | Daniel Cuc |  | 60 pcs sent to customer, rest remains in quaranteenn
G | RPP-K250045 | Ford | BEV-K 2P28S | H01 | Antonius Hutte | Rb part - welded, film | Thermal cycle test to Betrand | 6 |  | 2025-05-26 | 2025-06-19 | 2025-06-19 | Slavomir Majcher | film application and shipping CW25 | delay . Film for 2P28S was missing. CW24 received , GOM measurement of 6pcs shared with Bjorn
G | RPP-K250046 | Scania | GBP2 | A00 | Deng Guoyu | Rb Blank | Parts for customer 1 mm + 1 mm RB blank a RB Inf | 175 |  | 2025-07-24 | 2025-08-22 | 2025-08-22 | Daniel Cuc | Hole punching and inflation, then ship out | done
G | RPP-K250047 | Renault | Flex E-Van | F01 | Olivier Billot | Rb Inf | Parameter study inflation 2 | 20 |  | 2025-07-01 | 2025-07-31 | 2025-08-13 | Daniel Cuc | Get the report
G | RPP-K250048 | GM | Unknown | N/A | Lau Dan | Coupons | Material samples in US - second try | ?? |  | 2025-08-08 | 2025-09-02 | 2025-08-28 | Daniel Cuc |  | Shipped with Ibrahim out
G | RPP-K250051 | Renault | Flex E-Van | E00 | Oliver Flamm | Rb Blank | Test parts for Aachen | 35 |  | 2025-08-26 | 2025-09-10 | 2025-08-28 | Tomas Mesaros | Production finished, parts prepared in warehouse for shipping |  | Missing order! We had to scrap those pcs and then send
G | RPP-K250052 | Renault | Flex E-Van | E00 | Marek Drotar | Rb Blank | Unleveled parts for M.Drotar for testing | 20 |  | 2025-08-26 | 2025-09-12 | 2025-09-02 | Tomas Mesaros
Y | RPP-K250053 | CATL | 390-1 | A00 | Dominik Schutle | welding coupons | welding test in ATT | 150 |  | 2025-08-26 | 2025-08-28 | 2025-09-05 | Slavomir Majcher | Cutting 25 blanks NOK to get on support channel 6pcs 200x80 | Dominik will pick them up 28.8.2025, Agreed by Fabian for free
G | RPP-K250055 | Renault | Flex E-Van | E00 | Markus Wolf | Rb Blank | Parts after RB - Material thickness analysis | 6 |  | 2025-09-16 | 2025-09-16 | 2025-09-16 | Tomas Mesaros
Y | RPP-K250056 | CATL | 390-1 | A00 | Bjorn Scholemann | Rb Inf | Inf test, reflection, lab cut section test | 35 |  | 2025-09-01 | 2025-09-30 |  | Slavomir Majcher | Inf done, reflection done, lab measurement of cut secitions are pending
G | RPP-K250057 | Renault | Flex E-Van | E00 | Olivier Billot | Rb Part | Send 1 part for Ampere company | 1 |  | 2025-09-16 | 2025-09-17 | 2025-09-17 | Tomas Mesaros
Note on A8: R ... Order received Y ... Being processed G ... Done, results sent to orderer
Note on B8: Remi Beharel: TPP - tensioner prototype part T - Taicang 15 - Year 2015 xxxx - incoming number

## data
Customer | Project | Part | Worker | status
Mercedes | Showplate | Coupons | Daniel Cuc | R
Scania | Test Rack | Rb Part - coating | Slavomir Majcher | Y
Internal | Material test | Rb Inf | Marek Drotar | G
Ford | BEV-K 3P24S | Rb Blank | Tomas Mesaros | CANCELED
Renault | BEV-K 2P28S | Rb Blank + HP
Sunfire | BEV-K 2P36S | Rb Part
Audi | BEV-M | Other
GM | BEV-H | Rb Inf + cut for shipment
QMC | Flex E-Van | Rb Cut - scissors
Unknown | PVT Modul | Rp Part - welded spigots
CATL | SSP50A | Various
SK | Unknown | Rb CC
Volvo | Bionical Showplate | Rb LC
Samsung | C-EV | Rb part - welded, film
MOA | EX40 | Flat plates
Precitec | E092 | RB inf, film, inlays, w/o spigots
Internal | Gab-opening samples | RB inf, CC, w/o spigots
ReBuilt | 390-1 | spigots
TWL | GBP2 | welding coupons
PVT Flat
Slate
CATL

## BEVK DCV list
Updated: |  |  | 2025-06-26
BEV-K - Prototypes for customer - OVERVIEW
Number | Internal order number | Status | Product | Customer | Customer PO received | Amount | MDS Revision | Deviation to MDS | Required delivery from Kosice | PO number | Status now | Next process | Note | Estimated delivery ready | Delay in days | Delay accepted Y/N
1 | RPP-K250001K | Done | 2P36S | SK | YES | 86 | B01+I01 | coating | 2025-06-10 | 4200118980 | Shipped 86pcs | Assembly, Quality check, Shipping |  | 2025-07-08 | 28 | YES
2 | RPP-K250003K | Done | 2P36S | SK | YES | 76 | G01+J01 | With film | 2025-06-10 | 4200136384 | Shipped 76pcs | 14pcs still to be done -> Transferred to Nr6 | new PO pricing with film | 2025-06-12 | 2 | YES
3 | RPP-K250003K | Done | 2P28S | SK | YES | 96 | B01+H01 | With film | 2025-06-24 | 4200136384 | Shipped 96pcs | from 180 ps shipped 96 pcs, 69pcs missing PO, 15pcs new batch | new PO pricing with film | 2025-06-24 |  | YES
4 | RPP-K250003K | Done | 2P28S | SK | YES | 64 | B01+H01 | With film | 2025-06-24 | 4200136384 | Produced 69pcs | 69pcs received PO update - shipped 64pcs | received new PO pricing with film | 2025-07-17 | 23 | YES
5 | RPP-K250003K | Done | 2P36S | SK | YES | 155 | G01+J01 | With film | 2025-07-10 | 4200136384 | shipped | Available 155pcs Film, Assembly, Check, Shipping . Reat qty new batch | new PO pricing with film | 2025-07-17 | 7 | YES
6 | RPP-K250003K | Done | 2P36S | SK | YES | 163 | G01+J01 | With film | 2025-07-22 | 4200136384 | done , packed | Shipping on hold, deviation negotiation with customer SK | rest missing film- 23.7. delivered | 2025-09-30 | 70 | YES
7 | RPP-K250003K | Done | 2P28S | SK | YES | 19 | B01+H01 | With film | 2025-08-28 | 4200136384 | film application | Shipping on hold, deviation negotiation with customer SK | new PO pricing with film | 2025-09-30 | 33 | YES
8 | RPP-K250002K | Done | 2P36S | FORD | YES | 22 | B01+H01 | With film | 2025-09-04 | 4547223 | done , packed | Shipping on hold, deviation done with Ford |  | 2025-09-01 |  | YES
BEVK inventory CW33
\\group.mubea.net\fsgroup\KOS\LAUNCH_AND_PROTOTYPE_MANAGEMENT\01_Regular topics\04_Inventory\BEV K
MS Project planning
X:\KOS\LAUNCH_AND_PROTOTYPE_MANAGEMENT\01_Regular topics\09_Tracking\MS Project

## data_nemazať
Status | Internal order number | Customer | Project | MDS Revision | Submitted by | Product name | Purpose | Qty | Customer order number | Order date | Requested date | Delivered on | Worker | Next step | Remark | Lesson learnt from production built/Comment
G | RPP - K24010 | Ford | BEV-K 2P28S | TBS | Marcel Eifler | Rb Part - coating | 2P28S NOK with leak / no leak only channels and scrateches issue | 20 | 0 | 2024-12-10 | 2025-02-07 | 2025-02-25 | Slavomir Majcher | Prepared for shipping | Packed, prepared for shipping by DHL FORD - Georg needs to confirm PO | 0
G | RPP - K24011 | Ford | BEV-K 2P36S | TBS | Marcel Eifler | Rb Part - coating | 2P36S NOK with leak / no leak only channels and scrateches issue | 20 | 0 | 2024-12-10 | 2025-02-07 | 2025-02-25 | Slavomir Majcher | Prepared for shipping | Packed, prepared for shipping by DHL FORD - Georg needs to confirm PO | 0
G | RPP - K250002 | Ford | BEV-K 3P24S | N/A | Marcel Georg | Rp Part - welded spigots | Lennard COMP Parts , NOK but tight 3P24S | 8 | 0 | 2025-01-08 | 2025-01-24 | 2025-02-25 | Slavomir Majcher | shipping address to be clarified | DHL scheduled by FORD - Prepared for Lennard / FORD and packed 23.1.2025 | 0
G | RPP - K250003 | Ford | BEV-K 2P36S | N/A | Marcel Georg | Rp Part - welded spigots | Lennard COMP Parts , NOK but tight 2P36S | 7 | 0 | 2025-01-08 | 2025-01-24 | 2025-02-25 | Slavomir Majcher | shipping address to be clarified | DHL scheduled by FORD - Prepared for Lennard / FORD and packed 23.1.2025 | 0
G | RPP - K250006 | SK | BEV-K 2P36S | N/A | Marcel Georg | Rp Part - welded spigots | SK - not ordered yet – Additional Parts uncoated 2P36S | 20 | 0 | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV | 0
G | RPP - K250007 | Ford | BEV-K 3P24S | N/A | Marcel Georg | Rb Part - coating | FORD - 4499247- David Doman Parts - 3P24S | 63 | 0 | 2025-01-08 | 2025-03-21 | 2025-02-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | 0 | 0
G | RPP- K250004 | SK | BEV-K 2P36S | N/A | Marcel Georg | Rb Part - coating | 2P36S - PO 4200118980 /DCV/ -SK | 124 | 0 | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV | 0
Y | RPP- K250021 | Ford | BEV-K 2P36S | B01 | Marcel Georg | Rb LC | Special customer demand - different contour, no Inf, no welding | 12 | 0 | 2025-03-28 | 2025-09-23 |  | Slavomir Majcher | HP, laser cutting SLT different contour - Update (22.5.2025): missing customer PO - waiting for it - Update (4.6.2025): still waiting for PO - update 30.6.2025 : 2 pcs were sold for MOA shipped CW27 and 2pcs were sold for Precitec shipped CW29. Rest qty no PO yet. 4pcs are compleded to 12cps of qty CW38 | without PF,Inf, CC, welding . Only HP and separation , special contour Lacer cut | 0
CANCELED | RPP- K250022 | Ford | BEV-K 2P36S | B01 | Marcel Georg | Rb CC | Special customer demand - , no Inf, no welding - Fatugue test | 4 | 0 | 2025-03-28 | 2025-07-04 | 2025-09-17 | Slavomir Majcher | HP, CC - Update (22.5.2025): missing customer PO - waiting for it - Update (4.6.2025): still waiting for PO - Update (11.6.2025): still waiting for PO - on old | without PF,Inf, welding . Only HP and separation and CC | 0
G | RPP-K240001 | Scania | GBP2 | N/A | Deng Guoyu | Coupons | Samples for Att laser cut | 45 | 0 | 2024-12-05 | 2024-12-12 | 2024-12-11 | Daniel Cuc | 0 | Shipped WGM4489H together with Audi and Scania to SLT | 0
G | RPP-K240002 | Internal | Daimler Showplate | A06 | Marcel Eifler | RbPart - coating | Shanghai Autoshow exhibition | 10 | Kosice orders all | 2024-12-01 | 2025-02-15 | 2025-01-09 | Daniel Cuc | To be shipped back | Shipped to Weba | 0
G | RPP-K240003 | Mercedes | Test Rack | C00 | Robert Schneider | RbInf | Lab plates | 150 | 0 |  | 2025-02-07 | 2025-02-07 | Daniel Cuc | 0 | 0 | missing delivery note
G | RPP-K240004 | QMC | Unknown | E00 | Brian Wilson | Rb Inf + cut for shipment | B-samples | 150 | 0 | 2024-12-01 | 2024-12-19 | 2025-12-19 | Daniel Cuc | 0 | 150 parts shipped out in 5 boxes | 0
G | RPP-K240005 | CATL | Unknown | N/A | Deng Guoyu | Other | Material samples | 30 | 0 | 2024-12-02 | 2025-01-07 | 2025-01-07 | Daniel Cuc | 0 | Shipped out, delivery note in the folder | 0
G | RPP-K240006 | Internal | BEV-K 2P36S | B01 | Mike DeGregory | Rb Inf | 2P36S Engineering centre Auburn Hills | 300 | 0 | 2024-12-10 |  |  | Slavomir Majcher | start RB CW4 | open point - MDS DCV uppdate Mike De Gregory - approved serial B01(D01) | 0
G | RPP-K240007 | Ford | BEV-K 2P36S | TBS | Marcel Eifler | Rb Part - coating | 2P36S Customer | 500 | 0 | 2024-12-10 |  |  | Slavomir Majcher | start RB CW4 | open point - MDS Marcel Eifler - B01(D01) | 0
G | RPP-K24008 | Internal | BEV-K | N/A | Andreas Muller | Rb Inf | 2P36S NOK | 200 | 0 | 2024-12-13 | 2025-01-17 | 2025-01-14 | Slavomir Majcher | 0 | parts handed over to welding machines for trials | 0
G | RPP-K24009 | Internal | BEV-K | N/A | Marcel Eifler | Rb Inf | 2P36S NOK | 60 | 0 | 2024-12-17 | 2025-01-17 | 2025-01-21 | Slavomir Majcher | select parts and prepare for shipment | Sent to Kemper / batch to Vogler coating test/ | 0
G | RPP-K250001 | Internal | Material test | A00 | Lennart Rietz | Rb Blank | Test material 3D forming | 60 | 0 | 2025-01-07 | 2025-03-31 | 2025-04-04 | Daniel Cuc | 0 | sent on 4.4.2025 | MDS released without information, we were unable to use water inflation
G | RPP-K250005 | SK | BEV-K 2P28S | N/A | Marcel Georg | Rb Part - coating | 2P28S - PO 4200118980 /DCV/ -SK | 60 | 0 | 2025-01-08 | 2025-03-21 | 2025-04-10 | Slavomir Majcher | Production in hall 3 - tools validation needed | Cancelled by PM ,new planning DCV | 0
G | RPP-K250008 | Internal | Bionical Showplate | A00 | Frederik Schrewe | Rb Cut - scissors | Prototype showplatee Shanghai | 20 | 0 | 2025-12-09 | 2025-01-31 | 2025-02-07 | Daniel Cuc | get delivery note | 0 | too long plates, no packaging available
Y | RPP-K250009 | Internal | Renault | N/A | Bjoern/Markus Wolf | Rb Inf | For development department | 23 | 0 | 2025-01-10 | 2025-09-29 |  | Daniel Cuc | Send the parts A,B,C,D, G to measurement, rest plan for next Renault production - Update (4.6.2025): Email Conversation with Bjorn + Dan = we need to make it on next production loop (maybe July) - Update - run with next Renault production | Delivery date postponed to 15th February, due two updates and miscommunication | Wrong communication, many misunderstanding, clear process flow is necessary, 2 uncontroll updates
G | RPP-K250010 | Internal | BEV-K | B01 | Björn Scholemann | Various | 0 | 18 | 0 | 2025-01-15 | 2025-01-31 | 2025-03-25 | Daniel Cuc | Check where they are when come back from Attendorn | 0 | 0
G | RPP-K250011 | Internal | BEV-K 2P36S | B01 | Björn Scholemann | Rp Part - welded spigots | V29 HP tools test - ATT test of HP hole /penetration channels | 28 | 0 | 2025-01-31 | 2025-02-14 | 2025-03-13 | Slavomir Majcher | CW6.5 V29 tool broken / repair + spare partsreceived CW6 for test, PRO did leveling 10blanks CW6. HPtool test 10 blanksCW9.2 in Hall2 . Next PF/Inf/CC/weld - process flow hall3 | 0 | 0
G | RPP-K250012 | Internal | Renault | N/A | Marcel Eifler | Rb Blank | Renault 120blanks w/o screen print , leveled - old stock from hall4 | 120 | 0 | 2025-02-05 | 2025-02-14 | 2025-02-10 | Slavomir Majcher | Checked stock - 81 bl available 1520x1300 x 3 . Looks w/o - leveling done CW6 - PO Marcel E. | Checked stock - 81 bl available 1520x1300 x 3 . Needs to mesure tickness 1.2+1.5 | 0
G | RPP-K250013 | Internal | BEV-K 2P28S | N/A | Antonius Hutte | Rb CC | Demand 1+4 pcs for internal test from process flow hall3 | 5 | 0 | 2025-02-05 | 2025-02-14 | 2025-02-17 | Slavomir Majcher | sent 2 cut streap batches urgent to ATT by air CW6.5. Rest need to confirm by Antonius | Vulkan Engineering GmbH - 1 pc , Mubea Tailor Rolled Blanks GmbH z.Hd. Hütte, Antonius - 4 pcs | 0
G | RPP-K250014 | Internal | BEV-K 2P36S | N/A | Marcel Eifler | Rb CC | Internal test | 15 | 0 | 2025-02-06 | 2025-02-14 | 2025-02-10 | Slavomir Majcher | red area w/o spigot an lacer cut done - , CC will be in hall3 CW7 | NOK 15pcs 28S or 36S coling plates w/o spigot demand , CC or laser cut demand needs to check from Marcel | 0
CANCELED | RPP-K250015 | Internal | BEV-M | N/A | Björn Scholemann | Various | Investigation Holepunching; BEV-M; 0.5mm groove depth | 28 | 0 | 2025-02-05 | 2025-02-28 | 2025-04-03 | Daniel Cuc | 0 | 0 | canceled, not even knowing how
G | RPP-K250016 | Renault | Flex E-Van | N/A | Olivier Billot | Coupons | Coupons for customer | 30 | 0 | 2025-03-03 | 2025-07-23 | 2025-07-24 | Daniel Cuc | parts shipped out to customer | each part has differrent process | 0
G | RPP-K250017 | Internal | BEV-M | N/A | Bjoern Scholemann | Rb Inf | Leveling investigatin, various configurations based on list | 20 | 0 | 2025-01-09 | 2025-03-06 | 2025-03-10 | Daniel Cuc | 0 | Confirmation about shipment missing due to system not set up yet | parts lost, then found again due to no activity, need better tracking
G | RPP-K250018 | Volvo | EX40 | A00 | Julian Sieler | Rb Inf | Customer part presentation | 15 | 0 | 2025-03-19 | 2025-04-09 | 2025-04-04 | Daniel Cuc | 0 | sent on 4.4.2025 | parts lost, then found again due to no activity, need better tracking
G | RPP-K250019 | GM | Material test | N/A | Raneem | Coupons | Material samples in US | 15 | 0 | 2025-03-19 | 2025-04-09 | 2025-04-04 | Daniel Cuc | sent on 4.4.2025 - Update (22.5.2025): need to separate cupons - Update (4.6.2025): we will cut on Friday (6.6.2025) and after that send it Raneem - Update (10.6.2025): coupons are deburred and ready to shipping - waiting for PO from Raneem | 0 | well communicated from US, smooth production
G | RPP-K250020 | Ford | BEV-M | C00 | Marcel Eifler | Rb Blank | Parts without screen prints | 50 | 0 | 2025-03-26 | 2025-04-09 | 2025-04-01 | Daniel Cuc | 0 | Delivered to Marcel Eiffler | parts lost, then found again due to no activity, need better tracking
G | RPP-K250023 | Internal | Flex E-Van | F01 | Li Lei | Rb Blank | RB speed 12m/min, detailed analysis | ?? | 0 | 2025-04-09 | 2025-04-25 | 2025-05-27 | Marek Drotar | Receive instruction from Li Lei, Update (22.5.2025): Due date: 23.5.2025 | Marek Drotar has made the parts during the run for himself and tested furter | 0
G | RPP-K250024 | Internal | Flex E-Van | F01 | Kevin Koch | Rb Inf | Parameter study inflation | 30 | 0 | 2025-04-29 | 2025-05-30 | 2025-06-19 | Daniel Cuc | Production after R@R on HP+Inflation 28.5.2025 - Update (4.6.2025): Lab works on these pieces - deadline 17.6.2025 - maybe possible earlier 13.6.2025 - Update (19.6.2025): Petra sent email (12:57) about updated study of the inflation parameters | 0 | 0
G | RPP-K250025 | Internal | Flex E-Van | F01 | Markus Wolf | Rb Part | Corrosion test | 5 | 0 | 2025-03-20 | 2025-07-15 | 2025-07-31 | Daniel Cuc | Parts finishted, receive PO from Markus Wolf, prepare for shipment | 0 | Missing order even after the parts are produced
G | RPP-K250026 | Renault | C-EV | A00 | Olivier Billot | Rb Inf | Acquision parts | 100 | 0 | 2025-05-01 | 2025-07-24 | 2025-08-15 | Daniel Cuc | Mesurement on GOM done, parts arrived by customer | 0 | 0
G | RPP-K250027 | Samsung | E092 | A00 | Robert Schneider | Rb Inf | Acquision parts | 20 | 0 | 2025-05-29 | 2025-06-30 | 2025-06-30 | Daniel Cuc | 0 | 0 | 0
G | RPP-K250028 | Internal | Gab-opening samples | A00 | Robert Schneider | Rb Inf | Process Development Material | 20 | 0 | 2025-05-29 | 2025-06-30 | 2025-07-03 | Daniel Cuc | RB scheduled for week 24 | 0 | 0
G | RPP-K250029 | Internal | PVT Flat | 0 | Marek Drotar | Rb Blank | Material reduction during bonding | 10 | 0 | 2025-06-02 | 2025-07-03 | 2025-07-03 | Tomas Mesaros | Arrange RB with BEV-K, arrange PO - Update (11.6.2025) - waiting for RB BEV-K - 01.07.2025 changed to PVT flat, worker Tomas Mesaros | 0 | 0
G | RPP-K250030 | Mercedes | Test Rack | C00 | Robert Schneider | Rb Inf | Parts for customer - second batch | 50 | 0 | 2025-05-15 | 2025-07-01 | 2025-07-01 | Daniel Cuc | Shippment 1.7., save document | 0 | 0
G | RPP-K250031 | TWL | PVT Flat | A01 | Mike DeGregory | Rb Part | Parts for customer - PVT Flat Neumann | 150 | 0 |  | 2025-07-25 | 2025-08-01 | Tomas Mesaros | - Update (24.6.2025): MDS review | 0 | 0
Y | RPP-K250032 | CATL | 390-1 | A00 | Deng Guoyu | Rb Inf | Parts for customer and first trial | 50 | 0 | 2025-06-19 | 2025-09-15 |  | Slavomir Majcher | 3rd run - inflating parts, delivery date extended. Issue with channel burst and tinning . Inf Investigation . 24pcs inf done | 0 | 0
G | RPP-K250033 | Scania | GBP2 | A00 | Deng Guoyu | Rb Inf | Parts for customer | 100 | 0 | 2025-06-19 | 2025-07-31 | 2025-07-24 | Daniel Cuc | Parts delivered, done | 0 | 0
G | RPP-K250034 | 0 | PVT Flat | A02 | Mike DeGregory | Rb Part | Parts for customer - PVT Flat Flamm | 25 | 0 |  | 2025-07-25 | 2025-08-26 | Tomas Mesaros | - Update (24.6.2025): MDS review | 0 | 0
G | RPP-K250035 | 0 | PVT Flat | N/A | Marek Drotar | Rb Blank | Minimal roll reduction test | 0 | 0 |  | 2025-07-11 | 2025-07-03 | Tomas Mesaros | - Cooperation with Marek | 0 | 0
G | RPP-K250037 | MOA | BEV-K 2P36S | N/A | Marcel Georg | RB inf, CC, w/o spigots | Customer welding test | 10 | 0 | 2025-06-23 | 2025-07-03 | 2025-07-08 | Slavomir Majcher | packing, Shipping CW27 | 0 | 0
G | RPP-K250038 | Precitec | BEV-K 2P36S | N/A | Marcel Georg | RB inf, film, inlays, w/o spigots | Customer special demand | 6 | 0 | 2025-06-23 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | cleaning, film, inlys, qc, shipping CW29 | 0 | 0
G | RPP-K250039 | Internal | BEV-K 2P28S | N/A | Mike DeGregory | Rp Part - welded spigots | NOK parts for suppliers | 5 | 0 | 2025-06-30 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | goining to ship to ATT CW29 | 0 | 0
G | RPP-K250040 | Internal | BEV-K 2P36S | N/A | Mike DeGregory | Rp Part - welded spigots | NOK parts for suppliers | 5 | 0 | 2025-06-30 | 2025-07-10 | 2025-07-15 | Slavomir Majcher | goining to ship to ATT CW29 | 0 | 0
Y | RPP-K250041 | SK | BEV-K 2P36S | H01 | Marcel Georg | Rb Part | Parts with NOK film simulation for customer _ film issue validation | 10 | 0 | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | missing PO - free demand - on hold - negotiation wit customer | 0 | Still missing for PO. Long time waiting (1month)
Y | RPP-K250042 | SK | BEV-K 2P36S | N/A | Marcel Georg | spigots | Short spigots for customer welding test | 35 | 0 | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | Missing PO - on hold - negotiation price with cutomer | 0 | Still missing for PO. Long time waiting (1month)
Y | RPP-K250042 | SK | BEV-K 2P36S | N/A | Marcel Georg | spigots | Long and 35pcs short spigots for customer welding test | 35 | 0 | 2025-06-10 | 2025-09-30 |  | Slavomir Majcher | Missing PO - on hold - negotiation price with cutomer | 0 | Still missing for PO. Long time waiting (1month)
G | RPP-K250043 | Renault | Flex E-Van | N/A | Olivier Billot | Coupons | Coupons for customer | 50 | 0 | 2025-07-14 | 2025-07-30 | 2025-07-24 | Daniel Cuc | parts shipped out to customer | 0 | 0
G | RPP-K250044 | ReBuilt | Slate | 0 | Brian Wilson | Rb Inf | Parts for customer | 0 | 0 | 2025-07-14 | 2025-08-29 | 2025-09-03 | Daniel Cuc | 0 | 60 pcs sent to customer, rest remains in quaranteenn | 0
G | RPP-K250045 | Ford | BEV-K 2P28S | H01 | Antonius Hutte | Rb part - welded, film | Thermal cycle test to Betrand | 6 | 0 | 2025-05-26 | 2025-06-19 | 2025-06-19 | Slavomir Majcher | film application and shipping CW25 | delay . Film for 2P28S was missing. CW24 received , GOM measurement of 6pcs shared with Bjorn | 0
G | RPP-K250046 | Scania | GBP2 | A00 | Deng Guoyu | Rb Blank | Parts for customer 1 mm + 1 mm RB blank a RB Inf | 175 | 0 | 2025-07-24 | 2025-08-22 | 2025-08-22 | Daniel Cuc | Hole punching and inflation, then ship out | done | 0
G | RPP-K250047 | Renault | Flex E-Van | F01 | Olivier Billot | Rb Inf | Parameter study inflation 2 | 20 | 0 | 2025-07-01 | 2025-07-31 | 2025-08-13 | Daniel Cuc | Get the report | 0 | 0
G | RPP-K250048 | GM | Unknown | N/A | Lau Dan | Coupons | Material samples in US - second try | ?? | 0 | 2025-08-08 | 2025-09-02 | 2025-08-28 | Daniel Cuc | 0 | Shipped with Ibrahim out | 0
G | RPP-K250051 | Renault | Flex E-Van | E00 | Oliver Flamm | Rb Blank | Test parts for Aachen | 35 | 0 | 2025-08-26 | 2025-09-10 | 2025-08-28 | Tomas Mesaros | Production finished, parts prepared in warehouse for shipping | 0 | Missing order! We had to scrap those pcs and then send
G | RPP-K250052 | Renault | Flex E-Van | E00 | Marek Drotar | Rb Blank | Unleveled parts for M.Drotar for testing | 20 | 0 | 2025-08-26 | 2025-09-12 | 2025-09-02 | Tomas Mesaros | 0 | 0 | 0
Y | RPP-K250053 | CATL | 390-1 | A00 | Dominik Schutle | welding coupons | welding test in ATT | 150 | 0 | 2025-08-26 | 2025-08-28 | 2025-09-05 | Slavomir Majcher | Cutting 25 blanks NOK to get on support channel 6pcs 200x80 | Dominik will pick them up 28.8.2025, Agreed by Fabian for free | 0
G | RPP-K250055 | Renault | Flex E-Van | E00 | Markus Wolf | Rb Blank | Parts after RB - Material thickness analysis | 6 | 0 | 2025-09-16 | 2025-09-16 | 2025-09-16 | Tomas Mesaros | 0 | 0 | 0
Y | RPP-K250056 | CATL | 390-1 | A00 | Bjorn Scholemann | Rb Inf | Inf test, reflection, lab cut section test | 35 | 0 | 2025-09-01 | 2025-09-30 |  | Slavomir Majcher | Inf done, reflection done, lab measurement of cut secitions are pending | 0 | 0
G | RPP-K250057 | Renault | Flex E-Van | E00 | Olivier Billot | Rb Part | Send 1 part for Ampere company | 1 | 0 | 2025-09-16 | 2025-09-17 | 2025-09-17 | Tomas Mesaros | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0